## Deployment Plan
iComply Deployment Plan
PID | 302991
Release Date | 07/16/2021 (8:00 PM CT)
CR# | 6771971
Version Histoy
Date | Version No | Remarks | Updated By
2021-07-15 | 1 | Initial draft | tm682y

## Deployment Activity
Steps | Activity | Status | Owner | Estimated Time (mins) | Timings in CT
Step 1 | At least 2 hours before deployment time, send communication to PACE Team to disable adapters |  | DEV Team | N/A | 6:00PM
Step 2 | Check the CREATED_DATE of the latest PACE notification. If the create time is very close to the deployment time. Let's say less than 5 minutes, possible that the PACE adapters are still enabled. select * from (select * from PEDCOMP.COMPL_ASYNC_JOBS_QUEUE order by id desc ) where rownum = 1; |  | DEV Team | N/A | 8:00PM
Step 3 | Send outage communication to Business team |  | Mahesh | N/A | 8:30PM
Step 4 | Login to zlp08725.vci.att.com. Shut down iComply application. Take backup of crontab and Comment Below crons. a. /appl/PED/compl/scripts/OremisFeedManagement/OremisFeedManagement.sh b. /appl/PED/compl/scripts/CDMSFeedManagement/CDMSFeedManagement.sh c. /appl/PED/compl/scripts/RetrieveGuardianDataProcess/RetrieveGuardianDataProcess.sh d. /appl/PED/compl/scripts/inFlightCleanup/inFlightCleanup.sh e. /appl/PED/compl/scripts/InflightJob/InflightJob.sh f. /appl/PED/compl/scripts/InflightTask/InflightTask.sh g. /appl/PED/compl/scripts/TaskDetailsJobMonitor/TaskMonitor.sh h. /appl/PED/compl/scripts/ConnectDirect/connectdirect.sh i. /appl/PED/compl/scripts/UserManagement/UserManagement.sh |  | ENV Team | 15 | 9:00PM
Step 5 | Login to zlp08726.vci.att.com Shut down iComply application Take backup of crontab and Comment Below crons. a. /appl/PED/compl/scripts/CannedReportsGenerator/CannedReportsGenerator.sh b. /appl/PED/compl/scripts/TaskDetailsJob/TaskDetailsJob.sh c. /appl/PED/compl/scripts/TaskDetailsJobMonitor/TaskMonitor.sh |  | ENV Team | 10 | 9:15PM
Step 6 | Verify if application is down a. http://zlp08725.vci.att.com:8003/Compliance b. http://zlp08726.vci.att.com:8003/Compliance c. http://pedcomp.web.att.com/Compliance Verify if crons are disabled in logs |  | DEV Team | 5 | 9:25PM
Step 7 | Take Backup of current war file deployed in zlp08725.vci.att.com, zlp08726.vci.att.com |  | ENV Team | 10 | 9:30PM
Step 8 | Take backup of below mentioned deployment file(s) with folder name appended as “_backup_<date>” I. /opt/app/weblogic/12213/domains/complprod/servers/PEDCPLN_zlp08725/logs/PEDCPLN_zlp08725.out[zlp08725.vci.att.com] II. /opt/app/weblogic/12213/domains/complprod/servers/PEDCPLN_zlp08726/logs/PEDCPLN_zlp08726.out[zlp08726.vci.att.com] III. Compliance.war |  | ENV Team | 10 | 9:40PM
Step 9 | Deploy the following war file in Production for the Compliance app: https://codecloud.web.att.com/projects/ST_MNAT/repos/icomply/commits/704619b55e917ad27f4e0b742da01e59597db3f8 |  | ENV Team | 15 | 10:00PM
Step 12 | Execute script as PEDCOMP on P1C2D680. |  | DBA Team | 45 | 10:30PM
Step 13 | If taking DB backup and executing script are complete, start the compliance app in zlp08725.vci.att.com |  | ENV Team | 10 | 10:40PM
Step 14 | Enable commented crons in zlp08725.vci.att.com a. /appl/PED/compl/scripts/OremisFeedManagement/OremisFeedManagement.sh b. /appl/PED/compl/scripts/CDMSFeedManagement/CDMSFeedManagement.sh c. /appl/PED/compl/scripts/RetrieveGuardianDataProcess/RetrieveGuardianDataProcess.sh d. /appl/PED/compl/scripts/TaskDetailsJobMonitor/TaskMonitor.sh e. /appl/PED/compl/scripts/ConnectDirect/connectdirect.sh f. /appl/PED/compl/scripts/UserManagement/UserManagement.sh The following that must remain commented; a. /appl/PED/compl/scripts/CannedReportsGenerator/CannedReportsGenerator.sh b. /appl/PED/compl/scripts/inFlightCleanup/inFlightCleanup.sh c. /appl/PED/compl/scripts/InflightJob/InflightJob.sh d. /appl/PED/compl/scripts/InflightTask/InflightTask.sh |  | ENV Team | 10 | 10:50PM
Step 15 | Perform sanity on http://zlp08725.vci.att.com:8003/Compliance |  | DEV Team | 5 | 11:00PM
Step 16 | Start the compliance app in zlp08726.vci.att.com |  | ENV Team | 10 | 11:05PM
Step 19 | Enable commented crons in zlp08726.vci.att.com a. /appl/PED/compl/scripts/CannedReportsGenerator/CannedReportsGenerator.sh b. /appl/PED/compl/scripts/TaskDetailsJob/TaskDetailsJob.sh c. /appl/PED/compl/scripts/TaskDetailsJobMonitor/TaskMonitor.sh Run the script at /appl/PED/compl/scripts/CannedReportsGenerator/CannedReportsGenerator.sh and provide logs are running it. Run the script at /appl/PED/compl/scripts/TaskDetailsJob/TaskDetailsJob.sh and provide logs are running it. |  | ENV Team | 10 | 11:15PM
Step 20 | Perform sanity in on http://zlp08726.vci.att.com:8003/Compliance |  | DEV Team | 5 | 11:25PM
Step 21 | Peform Sanity on http://pedcomp.web.att.com/Compliance |  | DEV Team | 5 | 11:25PM
Step 22 | Validate deployed functionalities in zlp08725.vci.att.com (that could be tested) Validate items listed in Release Notes |  | DEV Team | 60 | 11:30PM
Step 23 | Validate deployed functionalities in zlp08726.vci.att.com (that could be tested) Validate items listed in Release Notes |  | DEV Team | 60 | 11:30PM
Step 24 | Validate deployed functionalities in load balancer url (that could be tested) Validate items listed in Release Notes |  | DEV Team | 60 | 11:30PM
Step 26 | Send out Business communication |  | Mahesh | N/A | 12:00PM
Step 27 | Send communication to PACE Team to enable adapters |  | DEV Team | N/A | 12:00PM

## Release Notes
No | Item Number | Status | Description | Priority | Assigned to | Type | Can be validated | Data | Results | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34

## Contacts
Dev | Mobile# | Email
Tanuj | 1 647-830-4835 | tm682y@att.com
IST
Nitish | 91 8108956958 | ni0631@att.com
Komal | 1 4705644059 | ks8426@att.com
BOA
Nikhil Mankar | 91 9960857071 | nm646c@att.com

## Rollback
Steps | Activity | Owner
Step 1 | Shut down iComply application in zlp08725.vci.att.com and zlp08726.vci.att.com | ENV Team
Step 2 | Deploy the backup taken for Compliance application in zlp08725.vci.att.com and zlp08726.vci.att.com | ENV Team
Step 3 | Deploy the backup taken for InflightJob in zlp08725.vci.att.com | ENV Team
Step 4 | Deploy the backup taken for TaskDetailsJob in zlp08726.vci.att.com | ENV Team
Step 5 | Start the Compliance application in zlp08725.vci.att.com and zlp08726.vci.att.com | ENV Team
Step 6 | Perform Sanity testing | DEV Team